## Sheet1
| Performance indicator: 2017/18 work plan | How we did | RAG
1 | Receive a minimum 25% increase in number of responses to our reflective review at the end of the year. | We received 149 responses compared to 90 last year so in numerical terms we have achieved this KPI. NB We went out to a much wider base (1315 compared to 293 in previous year). Therefore the response rate is lower but the number of responses is higher. We will review the learnings from this next time around.
2 | See an improvement in performance on relevant questions around perceptions of respect, trust and credibility in annual reflective review: increase in numbers rating core services as excellent or good; increase in number strongly agreeing or agreeing that HWSy is effective in encouraging commissioners and providers to value the involvement of local people Q17; increase in number saying significant or some influence in 6 areas of influence and impact. | Some questions added or change in the survey this year which makes direct comparison difficult. Over half of respondents ‘strongly agree’ or ‘agree’ that Healthwatch Surrey is a respected, trusted and credible champion for local people in health and social care in Surrey. Respondents were also asked whether ‘Healthwatch Surrey is effective in encouraging commissioners and providers to value the involvement of local people in the scrutiny and development of services’. A similar question was asked last year. In 2017 40% of respondents strongly agreed or agreed with the statement; in 2018 this has risen to 46% who strongly agreed or agreed.
3 | Monitor, report on and achieve high levels of satisfaction amongst those who use our services. | Achieved - Both the Helpdesk and IHCA have collected feedback from clients this year. Samples are small but feedback on both the Helpdesk and IHCA is very positive.
4 | Meet quarterly with CQC, have evidence to share and achieve demonstrable outcomes. | Achieved – see Outcomes report
5 | By end of year to be meeting with all CCGs on a quarterly basis, produce reports of our evidence to support these meetings and have sufficient experiences to support this. Have outcomes to demonstrate effectiveness. | Achieved for Guildford & Waverley; Surrey Downs; North West Surrey, Surrey Heath and East Surrey. Pogress in NEH&F has been slower - they haven't held meetings recently and it's complicated by overlap with Hampshire HW. We do however have lines of communcation for escalations and are in the process of setting up future meetings.
6 | Demonstrate that we have effective escalation routes for cases raised by the Escalations Panel and outcomes as a result. | Achieved; Escalations panel has been very succesful this year. See Outcomes report.
7 | Continue to capture outcomes across our work, report on these quarterly, and track these across the year. | Achieved see Outcomes report and this will be subject to review in 2018 to ensure we are using it to maximum effect as a comms tool.
8 | We will see increased awareness amongst the general public demonstrated by more people contacting us. We will achieve a 30% increase in web/social media traffic and a 25% increase in calls/emails to our helpdesk/enquiries. | Achieved for increase in web and social media traffic. More complicated for calls to Helpdesk and baseline for comparison to previous year is unclear. We now have firm figures for the year.
9 | We will see improved awareness amongst stakeholders measured by the 17/18 HWSy reflective review. | Achieved: awareness of the informatin and advice service has increased from just over a quarter in 2017 to just under half in 2018. The highest level of awareness is for Healthwatch Surrey’s work in gathering experiences and feedback, with almost two thirds of all respondents knowing ‘a lot’ or ‘a fair amount’. In 2017 around half of respondents knew about our evidence-gathering work.
10 | Achieve an increase in the number of experiences gathered outside of projects (from 2,693) | Achieved: we have gathered 3824 useable experiences overall this year
11 | Gather 100 experiences using a new more efficient method of engagement | Not achieved - made attempts through ‘Working Lunches’ with D&B councils but they did not go according to plan. Our emphasis on innovation in year ahead is around volunteer involvement in engagement
12 | Deliver 12 outputs and outcomes achieved related to thematic priorities | Achieved
13 | Achieve improvements in perceptions of stakeholders on our engagement, evidence, insight and influence according to reflective audit | There has been a reduction in the proportion of respondents giving a positive rating for all of the areas that were included in the 2017 survey. However, these ratings appear to have been skewed by the increased proportion of respondents from district and borough councils (who have not been Healthwatch Surrey’s ‘target’ for influence or impact). Health and social care commissioners, who we have specifically targetted, were more likely than last year to say that Healthwatch Surrey had some or significant impact across all core areas of our work, but most noteably around "improving services and making a difference for local people"; and "Taking action to address poor practice".
14 | Capture 50 experiences through Community Cash Fund and receive positive feedback from attendees at CCF Celebration event. | CCF Celebration seen as a great success. Number of expereinces not achieved although improvement on previous year. Subject to review this year.
15 | Have evidence that our volunteers report that being part of our project work is a good experience | Achieved – volunteer feedback has been sought after all project work. We can build on this further in 2018.
16 | Have one volunteer local team up and running and evaluation complete by October 2017. | Achieved – Surrey Heath team is up and running
17 | Assuming first local team is successful we will have two volunteer local teams up and running by end of year. . | Not achieved – Guildford and Waverley about to form but no others in pipeline at this stage. This is a key focus for 2018
18 | By the end of the year we will have developed and implemented a clear induction and training programme. | Not achieved across all areas of volunteering but plans in place which will be implemented when we have new staff member.
19 | Increase the number of volunteers making sure they are only in roles that meet the needs of Healthwatch Surrey and the volunteer. We will increase the total number of hours they are volunteering to 1250 hours a year. | Achieved - we counted 1,712 volunteer hours this year, excluding HEalthwatch Champions in the CABs and volunteers at our Helpdesk
20 | Implement proper support and management of all volunteers and recognition and rewards in order to retain existing and new volunteers. | Not achieved in full although had a very succesful Christmas party to thanks volunteers and all were thanked. Plans in place for recognition in 2018, linked to Volunteer Week in June, once we have new staff in post .
21 | Collect feedback from volunteers and we will receive positive feedback on their experience of volunteering with HWSy. | No formal feedback mechanism in place - need to do more in 2018, linked to Volunteer Week in June.
22 | Secure agreement from SCC to extend our contract from end March 2018. | Achieved
23 | Have a clear pitch for our offer, and staff team and board will be familiar with this and will be encouraged to take all opportunities to open discussions with potential clients. | Achieved although more needs to be done to refine the pitch building on learnings from work done this year.
24 | New business opportunities to be discussed as a standing item in staff team monthly meetings. | Achieved.
25 | Bring in a minimum of £25,000 in new income turnover this year, to fill the 5% reduction in our income from SCC. | Achieved.
26 | Develop a longer-term strategy for more ambitious income generation by end of Q3. | Not achieved as overtaken by Citizens Ambassador contract however plans are in place to review new business strategy in April 2018.
27 | We will ensure we have staff appraisal, development and training plans in place across the staff team and for our volunteers. | Achieved for staff. Work to do for volunteers - we plan to conduct full skills assessment and linked training once new staff in post.
28 | We will continue to seek out new accommodation. | Achieved; new accommodation sourced.
29 | We will review all policies and have a timetable for updating as necessary. | Achieved - policies reviewed and updated and on Sharepoint. We are now updating the information governance again due to the GDPR changes in May 2018.
30 | We will review HWSy Board development. | In progress.