## Sheet1
2017-2018 Work Plan Overview
| April | May | June | July | August | September | October | November | December | January | February | March
Care Homes | June: Impact Report Care Homes
Mental Health | April: Safe Havens Report; August: Impact Report Safe Havens
GP Access | May: GPs Report; July: Accessibility Guide
Hospital Discharge | April: Summary Report; September: Espom @ home evaluation
NHS Complaints
Thematic Priorities review | May: Thematic Priorities 19th Sub-Group; July: 25th HWSy Board
Comms Campaign | Discharge | GP's | Care Homes | HW Awareness | Complaints | TBC | Mental Health | Communications Strategy evaluation
Awareness Raising | April: Distribute literature to all PALs depts; May: sub-group; June: strategy development; presentation training; July: Radio Campaign
LHM Feedback Centre | April: Up and running end May
LHM New Website | August: Launch???
Engagement
Volunteer Strategy | April: Volunteer Strategy development; May: 9th HWSy Board; June: Implementation
Representation on Boards Strategy | April: Boards strategy development; June: 13th HWSy Board
VCFS Strategy | April: VCFS strategy development; May: 9th HWSy Board
New Business | April: 28th April Sub-Group; June: 13th HWSy Board
Annual Report | April: Annual Report Development; June: Annual Report published
Review Report Production | June: Review report production process
PPG's
Consultation Institute | July: Training
Reflective Audit | February: Reflective Audit
Community Cash Fund | May: Review new projects; July: 5th July launch new CCF; October: Celebration Event 5th Assessment- 19/10 Winners Workshop
Board Meetings | Public 25/4 | Private 9th | Private 13th | Public 25/7 | Private 15th | Private 12th | Public 24/10 | Private 14th | Private 12th | Public - tbc
2018/2019 Planning | January: Planning